LAWDECK

Build Phases

Version 1.1 · The order of work, and what “done” means for each phase

| Document control |  |
| --- | --- |
| Version | 1.1 (adds Stages A to C: before-code items, full checklist map, parallel work) |
| Date | 20 October 2026 |
| Based on | PRD v2.0; Engineering Rules v1.0; System Design v1.0 |
| Builder | Founder, building with Claude Code |

## How to use this document

- Work through the phases in order. Each phase ends with an exit checklist; do not start the next phase until every box is ticked, or an exception is written down.

- Inside each phase, build one feature at a time using the seven-step workflow in the Engineering Rules (spec, plan, small steps, test like a student, checklists, commit).

- Durations are rough estimates for one person building part-time with an AI coding tool. They will move; the exit checklists will not.

- Costs per phase follow the start-up cost estimate of 20 October 2026.

# Overview

| # | Phase | Result | Rough time | Cost / month |
| --- | --- | --- | --- | --- |
| 0 | Foundations | Accounts, repository, empty app online, Claude replies “OK” | 3–5 days | $5–10 |
| 1 | Shell, sign-in and data | Sign up, three-pane workspace, secure database | 2–3 weeks | $5–10 |
| 2 | Library and search | First course’s material searchable; reviewer approval | 2–3 weeks | $5–15 |
| 3 | Learn: ask and explain | Structured, sourced answers; model choice tested | 3–4 weeks | $10–20 |
| 4 | Practice | Questions, flashcards, marking, briefs | 2–3 weeks | $10–20 |
| 5 | Draft | Nigerian-format documents, preview, DOCX and PDF | 3–4 weeks | $10–20 |
| 6 | Uploads and sharing | Private uploads, sharing, account deletion | 1–2 weeks | $10–20 |
| 7 | Pre-pilot hardening | Payments, limits, backups, security, full library | 2–3 weeks | $50–60 |
| 8 | Closed pilot | 10–20 students, then a larger cohort; real costs measured | 4–6 weeks | $70–115 |

Total to a pilot-ready release: roughly 4–6 months part-time. Phases 2–5 start with one course (Civil Litigation) and widen to all five in Phase 7.

# Stage A. Before any code (completed)

Everything that had to be decided before the first line of code is done. These are the foundations every phase builds on.

| Item | Where it was settled | Status |
| --- | --- | --- |
| Product requirements | PRD v2.0 | Done |
| Engineering rules (how code is written) | Engineering Rules v1.0 and CLAUDE.md | Done |
| System design (the parts and how they connect) | System Design v1.0, sections 1–2 | Done |
| Data modelling (the tables) | System Design, section 3 | Done |
| Authorization (who can do what) | System Design, section 4 | Done |
| Database permissions (row-level security plan) | System Design, section 4.3 | Done |
| Environment variables (keys and settings list) | System Design, section 8.3 | Done |
| Mobile-first rule | Engineering Rules M-01; phone design | Done |
| Error-handling pattern | Engineering Rules I-01 to I-03 | Done |
| AI code security rules | Engineering Rules G-07, P-01, Appendix C | Done |
| Testing approach | Engineering Rules O-01 to O-06 | Done |
| AI provider | Claude (Anthropic); Voyage AI for search | Done |
| Interface design | Lawdeck UI Design canvas (six boards) | Done |
| Brand: logo, colours, fonts | Brand board: monochrome logo, Newsreader, Inter, Outfit | Done (vector logo redraw pending) |
| Cost model | AI Cost Model spreadsheet and explainer | Done (finance review pending) |
| Legal position | Counsel’s advice of 20 October 2026, in PRD section 9.1 | Done |
| Open items list | Open Items tab; PRD section 14 | Kept up to date |

# Stage B. The full checklist: where each item happens

Each item on the engineering checklist is designed once, built in a specific phase, and checked again later. Nothing is left to “someday”.

| Item | Designed (before code) | Built in | Checked again in |
| --- | --- | --- | --- |
| System design | Done: System Design | All phases follow it | End of every phase |
| Data modelling | Done: System Design §3 | Phases 1–6, tables added as features need them | Every phase (permission tests) |
| Authorization | Done: System Design §4 | Phase 1 | Phase 7 security review |
| Database permissions | Done: row-level security plan | Phase 1, then every new table | Every phase; Phase 7 review |
| Environment variables | Done: §8.3 list | Phase 0 | Phase 7 (separate staging and production keys) |
| Login | Rules C-01 to C-04 | Phase 1 | Phase 7 (login limits) |
| Mobile responsiveness | Rule M-01; phone design | Phase 1, then every screen | Every exit checklist |
| Error handling | Pattern I-01 | Phase 1, then every feature | Phase 7 (error monitoring) |
| AI code security | Rules G-07, P-01, Appendix C | Phase 0 (review every change); Phase 3 (prompt-injection guard) | Phase 7 security review |
| Testing | Rules O-01 to O-06 | Phase 1 (test tools); Phase 3 (AI evaluation) | Every exit checklist |
| Networking | Rules J-01 to J-03 | Phase 0 (HTTPS); Phase 3 (streaming, retries) | Phase 7 |
| Rate limiting | Rules K-01 to K-03 | Phase 0 (spending cap); Phase 3 (usage logging, basic limits) | Phase 7 (plan limits, login limits) |
| Performance | Rules L-01 to L-03 | Phase 1 (page budgets); Phase 3 (answer speed) | Phase 7 (load test) |
| Backups | Rules Q-01 to Q-03 | Phase 2 (library source store); Phase 7 (daily backups) | Phase 7 (restore test) |
| Data breach check | Rules P-02 to P-05; Appendix D | Phase 0 (secret scanning) | Phase 7 (monitoring, response plan) |

# Stage C. Work that runs alongside the code

These are not coding tasks, but phases depend on them. Start them now so they are ready when the phase needs them.

| Workstream | Who | Needed by |
| --- | --- | --- |
| Collect library material: notes from 2020 onward, course materials and drafts for all five courses | Founder | Civil Litigation by Phase 2; all courses by Phase 7 |
| Recruit legal reviewer(s) (lecturers or practitioners) | Founder and legal co-founder | Before Phase 2 |
| Write evaluation questions and pushback cases | Reviewer | Phase 3 |
| Write and approve rubrics | Reviewer | Phase 4 |
| Review document templates and court formats | Reviewer | Phase 5 |
| Finance review of the cost model | Finance and legal co-founder | Before Phase 3 model choice |
| Decide prices, free-tier limits and payment methods | Founders | Before Phase 7 |
| Choose payment provider | Founder | Before Phase 7 |
| Privacy Notice and Terms of Use | Legal co-founder | Before Phase 7 |
| Redraw the logo as a vector (SVG) file | Founder or designer | Before Phase 1 design tokens |
| Partnership: NBA Young Lawyers Forum, then the Council of Legal Education | Legal co-founder | Demonstration after Phase 5; formal approach in Phase 8 |
| Team members and hours (open item) | Founder | Ongoing; revisit before Phase 3 |

# Phase 0. Foundations

Goal: Every account and tool is in place, an empty Lawdeck app is online, and Claude answers a test message.

## Tasks

☐  Create the private GitHub repository lawdeck; turn on secret scanning and push protection (P-02).

☐  Add docs/ with the PRD, Engineering Rules, System Design and this document; add CLAUDE.md at the root (T-01).

☐  Create the Next.js app with TypeScript (strict) and Tailwind; set up the folder structure from the Engineering Rules (A-01, A-05).

☐  Create .env.example listing every variable; keep .env.local out of git (B-01 to B-03).

☐  Create a Supabase development project in a European region; switch on the pgvector extension.

☐  Connect the repository to Vercel; every pull request gets a preview link (R-02).

☐  Create the Anthropic developer account; load $5–10; set a $20 monthly limit and alerts (K-03).

☐  Create the Voyage AI account and key.

☐  Build the health check: a page that asks Claude “Reply with OK” through src/server/ai and shows the reply.

☐  Set up the branch habit: one feature per branch, merge by pull request (S-01 to S-03).

## Rules that apply from this phase

Code structure (A), secrets and environment variables (B), dependencies (D-01), Git workflow (S), documentation (T), secret scanning (P-02), AI module (G-01).

## Exit checklist (all must be true)

☐  The app is live on a Vercel address and shows a placeholder home page.

☐  The health check shows Claude’s reply; the API key is not visible anywhere in the browser.

☐  No secrets in the repository (secret scanning is on and clean).

☐  CLAUDE.md and the four documents are in the repository.

Note Use the free plans of GitHub, Vercel and Supabase. The only payment is the first Claude credit.

# Phase 1. Shell, sign-in and data foundation

Goal: A student can sign up, sign in and see the calm three-pane workspace on a phone and a computer, on top of a secure database.

## Tasks

☐  Design tokens: colours, spacing, type, light and dark themes (M-03).

☐  Three-pane shell: left navigation, middle work area, right panel (closed by default); collapses correctly at 1024 px and 768 px (WS-01, M-01).

☐  Input-first home: greeting, composer, mode selector (Auto, Learn, Draft), course selector, attach button; no AI yet (WS-02).

☐  Sign-in with Supabase Auth: email and password with verification, Google sign-in, password reset (C-01 to C-03, AC-01).

☐  First migrations: profiles (with role), plans, projects, conversations, messages, courses, topics, usage_events, audit_log, all with row-level security (E-03, N-01 to N-03).

☐  Permission tests: two test students cannot see each other’s rows (E-06, O-02).

☐  Standard error pattern and loading, empty and error states (I-01, I-02).

☐  Test tools set up (Vitest, Playwright); tests run on every pull request (O-01, O-03, O-05).

☐  Dependency security check on pull requests (D-03).

☐  Projects: create, rename, delete; chats listed in the left pane (WS-05).

## Rules that apply from this phase

Authentication (C), authorization and database permissions (E), validation (F-01, F-04), errors and logging (I-01 to I-03), mobile, accessibility and design (M), data modelling (N), testing (O-01 to O-03, O-05), dependencies (D-02, D-03).

## Exit checklist (all must be true)

☐  Sign up, verify email, sign in, sign out and reset password all work.

☐  Workspace looks right and is usable at 360 px, 768 px, 1024 px and desktop widths; keyboard only works.

☐  Every table has row-level security; permission tests pass.

☐  Home page loads in under 3 seconds on a throttled 4G connection.

# Phase 2. Library and search

Goal: The first course’s material (Civil Litigation) is in the library, reviewed, and searchable by meaning and by exact words.

## Tasks

☐  Migrations: kb_items, kb_passages with metadata, review status and embedding model (H-02).

☐  Admin upload screen for library files with their details; files stored in the private library bucket.

☐  Text extraction, OCR for scans, splitting into passages with headings and page numbers.

☐  Embeddings with Voyage AI; test the general and legal models on 30 Civil Litigation questions and record the choice.

☐  Hybrid search (meaning + keywords), filtered by course and approval status in the database.

☐  Reviewer console: list items, view passages, approve, correct, reject, withdraw; record reviewer and date (H-05, FB-02).

☐  Currency flag: items older than a later change in the law they discuss are marked for review (KB-02).

☐  Load and review the Civil Litigation material (notes from 2020 onward, course materials, drafts, rules of court).

☐  Keep the original source files in a separate versioned store (Q-03).

## Rules that apply from this phase

Knowledge base (H), retrieval permissions (E-04), upload validation (F-02), no legal content in code (H-01).

## Exit checklist (all must be true)

☐  Civil Litigation material is loaded, and every item shown to students is approved.

☐  For 30 test questions, the right passage appears in the top results at least 25 times.

☐  Unapproved and withdrawn items never appear in search results (tested).

☐  The embedding model choice is recorded with the test results.

# Phase 3. Learn: ask and explain

Goal: A student asks a Civil Litigation question and gets a clear, structured, sourced answer that streams in, with honest limits.

## Tasks

☐  Prompt files for explanations, with the answer structure and the behaviour rules (correct, hold position, accept valid correction) (G-02).

☐  Explain flow: retrieve, build prompt, stream answer, save message and sources (LN-01, LN-03).

☐  Sources panel: clicking an authority opens its passage in the right panel (WS-04).

☐  Citation check and 50-word quote limit on every answer (G-04, G-05).

☐  “Not enough support” response when passages cannot support an answer (LN-04).

☐  Simple and Exam-ready levels (LN-02); course hubs listing topics (LN-05).

☐  Auto mode routing with Haiku and the “Treated as” chip (WS-03).

☐  Usage logging per call, and per-user limits checked before each call (G-08, K-01 groundwork).

☐  Evaluation set v1 for Civil Litigation: at least 40 questions plus pushback cases, reviewed by a legal reviewer (O-04, O-06).

☐  Model quality test: run the evaluation with Haiku, Sonnet and Opus for explanations; choose by quality and cost; update the cost model.

## Rules that apply from this phase

AI rules (G-01 to G-10), prompt injection protection (G-07), no personal data to Claude (G-06), networking and streaming (J), performance budgets (L-01, L-02), AI evaluation and pushback tests (O-04, O-06).

## Exit checklist (all must be true)

☐  Zero fabricated authorities on the Civil Litigation evaluation set.

☐  At least 85% of evaluation answers rated “approved” by the reviewer.

☐  All pushback cases pass (corrects, holds, rejects fake authority, accepts valid correction).

☐  First words of an answer appear within 3 seconds (median).

☐  The explanation model is chosen and the cost per message is measured.

# Phase 4. Practice

Goal: Students can practise with questions and flashcards, get their answers marked, and read case and statute briefs.

## Tasks

☐  Migrations: practice_sets, practice_items, rubrics, attempts.

☐  Practice questions (multiple choice and scenario) by course and topic (LN-06).

☐  Flashcards with known and unknown tracking (LN-07).

☐  Rubrics written and approved for Civil Litigation topics (with the reviewer).

☐  Mark my answer: typed or uploaded answer, structured feedback in the right panel (LN-08).

☐  Case and statute briefs (LN-09).

☐  Marking agreement test: 50 answers marked by Lawdeck and by the reviewer.

## Rules that apply from this phase

AI output validation (F-03), structured results, all earlier rules.

## Exit checklist (all must be true)

☐  Lawdeck’s marking agrees with the reviewer on at least 80% of rubric points.

☐  Questions and flashcards cite only library material.

☐  All practice data passes the two-student permission tests.

# Phase 5. Draft: Nigerian-format documents

Goal: A student asks for a Civil Litigation or Property Law document and gets it laid out correctly, previewed as pages, and exported to DOCX and PDF.

## Tasks

☐  Migrations: forums, templates, documents, document_versions.

☐  Template and forum-profile schemas; validation before approval (H-03).

☐  One renderer for preview and DOCX (H-04); PDF converter running locally, then hosted.

☐  Draft flow: identify document, choose court or registry, intake questions, Opus fills narrative fields, placeholders for missing facts (DR-02 to DR-04).

☐  Automatic checks: parts, names, dates, defined terms (DR-06).

☐  Preview panel as A4 pages; edit in the panel or by instruction; versions (DR-05).

☐  “Why is it arranged this way?” explanations (DR-08) and related documents for a Lagos writ (DR-09).

☐  First templates, reviewed by a legal reviewer: writ of summons, statement of claim, motion on notice with affidavit, deed of assignment, tenancy agreement.

☐  Export tests: DOCX opens correctly in Word and Google Docs; PDF matches preview.

## Rules that apply from this phase

Templates as data (H-03), one renderer (H-04), unreviewed content never shown (H-05).

## Exit checklist (all must be true)

☐  Five templates approved by a reviewer, each with its rule source and review date.

☐  “Draft a writ of summons” produces a correct writ in the panel within 30 seconds.

☐  No generated document contains an invented party, date or property detail.

☐  Exported DOCX and PDF match the preview page for page.

# Phase 6. Uploads, sharing and account controls

Goal: Students can upload their own study material privately, share documents view-only, and delete their account.

## Tasks

☐  Upload notice shown before first upload (UP-06).

☐  Private uploads: storage folder rules, extraction, passages tied to owner (UP-01 to UP-05).

☐  Answers label “From your uploads” versus “From the Lawdeck library”.

☐  Sharing: view-only links, list of who has access, revoke (EX-04).

☐  Export notes, briefs and flashcards (EX-03).

☐  Delete account and data (AC-05); report a problem (FB-01); takedown request route (FB-03).

## Rules that apply from this phase

Upload validation (F-02), storage rules (E-03), prompt injection protection for uploads (G-07).

## Exit checklist (all must be true)

☐  A second student can never retrieve, see or be answered from another student’s upload (tested).

☐  Revoking a share stops access immediately.

☐  Deleting a file removes it from search within 5 minutes.

# Phase 7. Pre-pilot hardening

Goal: Lawdeck is safe, affordable and complete enough for real students.

## Tasks

☐  Move to Supabase Pro and Vercel Pro; create staging and production environments with separate keys (B-04, R-01).

☐  Payments with a Nigerian provider; plans and limits enforced (AC-03, AC-04, K-01).

☐  Login, sign-up and reset limits (C-04, K-02).

☐  Daily backups and a practice restore into staging (Q-01, Q-02).

☐  Error monitoring and unusual-access alerts (I-04, P-03).

☐  Breach response plan finalised (P-04, Appendix D).

☐  Security review of permissions, secrets and uploads (P-05).

☐  Load test for 500 concurrent users (L-03).

☐  Privacy Notice and Terms of Use reviewed by counsel; consent at sign-up.

☐  Library, rubrics and templates for all five courses loaded and approved.

☐  Full evaluation set (150+ questions, 30 drafting requests) passes all launch gates.

## Rules that apply from this phase

All remaining “Pre-pilot” rules: C-04, I-04, K-01, K-02, L-03, P-03 to P-05, Q-01, Q-02.

## Exit checklist (all must be true)

☐  Every PRD launch gate in section 11 is met.

☐  A restore from backup has been completed successfully.

☐  Security review findings are fixed.

☐  Prices and free-tier limits are set using the cost model and measured costs.

# Phase 8. Closed pilot

Goal: Real Law School students use Lawdeck; we learn what works, what it costs and what they will pay.

## Tasks

☐  Invite 10–20 students (start with resit candidates or recent finalists), then widen to a cohort.

☐  Weekly review of problem reports, evaluation results and costs.

☐  Measure: weekly active students, messages per student, cost per student, marking agreement, document use.

☐  Interview pilot students on value and price.

☐  Prepare the demonstration for the Council of Legal Education through the NBA Young Lawyers Forum.

## Rules that apply from this phase

All rules apply. No feature merges without the full definition of done.

## Exit checklist (all must be true)

☐  At least 40% of pilot students still active in week 4.

☐  At least 15% of pilot users willing to pay at the tested price.

☐  Real cost per student is known and within the target share of price.

☐  A go / revise / stop decision is recorded.

# When each Engineering Rule takes effect

| Phase | Rules |
| --- | --- |
| 0 Foundations | A-01 to A-07, B-01 to B-03, B-05, D-01, G-01, P-01, P-02, R-02, S-01 to S-03, T-01, T-02 |
| 1 Shell, sign-in, data | C-01 to C-03, D-02, D-03, E-01 to E-03, E-05, E-06, F-01, F-04, I-01 to I-03, M-01 to M-03, N-01 to N-04, O-01 to O-03, O-05, T-03 |
| 2 Library and search | E-04, F-02, H-01 to H-03, H-05, Q-03 |
| 3 Learn | F-03, G-02 to G-10, J-01 to J-03, K-03, L-01, L-02, O-04, O-06 |
| 5 Draft | H-04 |
| 7 Pre-pilot | B-04, C-04, I-04, K-01, K-02, L-03, P-03 to P-05, Q-01, Q-02, R-01 |

Once a rule takes effect it applies to all later work. Rules labelled “Phase 1” in the Engineering Rules (meaning the first build stage) are spread across Phases 0–3 here; separate staging keys and environments (B-04, R-01) wait until Phase 7, when real users arrive.